## CDN Transition Plan
|  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November |  |  |  |  | December
|  |  | 3 | 10 | 17 | 24 | 31 | 7 | 14 | 21 | 28 | 5 | 12 | 19 | 26 | 2 | 9 | 16 | 23 | 30 | 7 | 14 | 21 | 28
Task | Sub-task | Team/Owner
Review Highwinds CDN offering |  | All | bar: August 3 to August 31
Transition plan review and agreed by all parties |  | Chris | bar: August 31
Create relevant accounts and permissions in StrikeTracker |  | Javier | bar: August 31
Identify all active campaigns scheduled to run past 08/30 | Send out results to appropriate stakeholders | Jaladhi | bar: September 7
Identify all active campaigns scheduled to expire prior to 08/30 | Send out results to appropriate stakeholders | Jaladhi | bar: September 7
Set up any required training sessions with Highwinds for StrikeTracker | Call Highwinds for availability | Chris | bar: August 31
| Remote training session/Q&A | Highwinds | bar: September 7
Configure automated back-up of origin files from CDN | At least nightly, preferably every hour or two to long term storage | Richard
Please also look into the StrikeTracker API to ascertain whether we can perform deltas rather than full back-ups
Long running campaigns transistioned to Highwinds CDN | Reconfigure any asset pointers in reflex or templates to point to cdn.mediabrix.com | Javier/Johnathan/AdOps | bar: September 21 to October 5
| Verify asset pointers work as expected | Johnathan/AdOps | bar: September 21 to September 28
| Spot check and monitor asset delivery | Javier/Johnathan/AdOps | bar: October 5 to October 26
New campaigns now hosted from Highwinds CDN | Any new assets will be hosted directly from Highwinds CDN | Johnathan | bar: September 7 to October 26
| Spot check and monitor asset delivery | Javier/Johnathan/AdOps | bar: September 7 to October 26
Sanity check all templates and custom code | Ensure there are no hard-coded urls pointing to Limelights CDN | Lee/Johnathan/Jaime B | bar: September 14 to September 21; October 12 to October 19
Notify Limelight |  | Chris/Aaron | bar: August 31
Limelight CDN is decomissioned | bar: November 2